## Feuille1
Categorie	Sous-categorie	Sous-categorie 2	Detail	Temps	Avancement	Temps passe	Reste	Qui?	Progression
POSTGRES	créer database	immo	immo	5	100%	5	0	MHR	88.43%
POSTGRES	créer table	habitation	id, nom,idCategorie, nb chambre, loyer, quartier, descri, idphoto a la une	2	100%	2	0	H
POSTGRES	créer table	photo	id, idhabitation, repertoire	2	100%	2	0	H
POSTGRES	créer table	utilisateur	id, email, nom, mdp, tel, isadmin	2	100%	2	0	H
POSTGRES	créer table	reservation	id, datearrivee, datedepart, idhabitation	2	100%	2	0	H
POSTGRES	créer table	categorie	id, nom	2	100%	2	5	H
POSTGRES	insertion donnee de test	habitation		10	100%	10	0	H
POSTGRES	insertion donnee de test	photo		20	100%	20	0	H
POSTGRES	insertion donnee de test	user		2	100%	2	0	H
POSTGRES	insertion donnee de test	reservation		7	100%	7	0	H
POSTGRES	insertion donnee de test	categorie		5	100%	5	0	H
Page	login	email, mdp	conception	6	100%	6	0	MHR
Page	login	email, mdp	html	10	100%	10	0	M
Page	login	email, mdp	css	30	100%	30	0	R
Page	login	email, mdp	dynamisation	10	100%	10	0	H
Page	admin	Lister , modif, supp, ajouter habitat	conception	12	100%	12	0	MHR
Page	admin	Lister , modif, supp, ajouter habitat	html	10	100%	10	0	M
Page	admin	Lister , modif, supp, ajouter habitat	css	30	100%	30	0	R
Page	admin	Lister , modif, supp, ajouter habitat	dynamisation	10	100%	10	0	H
Page	admin	modifier	conception	5	100%	5	0	MHR
Page	client	liste	conception	6	100%	6	0	MHR
Page	client	liste	html	5	100%	5	0	M
Page	client	liste	css	30	100%	30	0	M
Page	client	liste	dynamisation	5	100%	5	0	R
Page	client	detail, reservation	conception	6	100%	6	0	MHR
Page	client	detail, reservation	html	10	100%	10	0	M
Page	client	detail, reservation	css	30	100%	30	0	HR
Page	client	detail, reservation	dynamisation	10	100%	10	0	R
Page	admin	evolution nb d’habitat/jour	conception	6	100%	6	0	MHR
Page	admin	evolution nb d’habitat/jour	html	10	100%	10	0	M
Page	admin	evolution nb d’habitat/jour	css	10	100%	10	0	H
Page	admin	evolution nb d’habitat/jour	dynamisation	30	100%	30	0	H
Page	admin	Evolution loyer/jour	conception	6	100%	6	0	MHR
Page	admin	Evolution loyer/jour	html	5	100%	5	0	M
Page	admin	Evolution loyer/jour	css	10	100%	10	0	H
Page	admin	Evolution loyer/jour	dynamisation	15	100%	15	0	H
Page	client	occupation logement	conception	6	100%	6	0	MHR
Page	client	occupation logement	html	10	100%	10	0	M
Page	client	occupation logement	css	10	100%	10	0	H
Page	client	occupation logement	dynamisation	30	100%	30	0	H
PHP	fonction	insert user	email, nom, mdp, tel, isadmin	5	50%	5	0	R
PHP	fonction	verifier login	User / null	6	50%	6	0	R
PHP	fonction	insert habitat	insert habitat	3	50%	3	0	R
PHP	fonction	insert photo	idhabitation, repertoire	0	50%	0	0	R
PHP	fonction	getAllHabitat	idCategoie habitat	5	50%	5	0	R
PHP	fonction	getAllPhotos	idhabitat	1	50%	1	0	R
PHP	fonction	search	string: descri -> habitation[ ]	1	50%	1	0	R
PHP	fonction	getHabitat	idhabitat	2	50%	2	0	R
PHP	fonction	modifier	idhabitat	3	50%	3	0	R
PHP	fonction	supprimer	iidhabitat	2	50%	2	0	R
PHP	fonction	insert reservation	datearrivee, datedepart, idhabitation	1	50%	1	0	R
PHP	fonction	getNbHabitatJour	date	5	50%	5	0	R
PHP	fonction	getMontantLoyerJour	date	1	50%	1	0	R
PHP	fonction	getOccupaLogement	date	1	50%	1	0	R
PHP	test	fonctions		20	50%	20	0
POSTGRES	requete	getAllHabitat	idCategorie	1	100%	1	0	H
POSTGRES	requete	search	by description	1	100%	1	0	H
POSTGRES	requete	getHabitat	by id habitation	1	100%	1	0	H
POSTGRES	requete	modifier	categorie, nb chambres, loyer, descri, quartier where idHabitat	2	100%	2	0	H
POSTGRES	requete	supprimer		2	100%	2	0	H
POSTGRES	requete	insert reservation		1	100%	1	0	H
POSTGRES	requete	getNbHabitatOQPJour	by date	2	100%	2	0	H
POSTGRES	requete	getMontantLoyerJour		2	100%	2	0	H
POSTGRES	requete	getOccupaLogement		10	100%	10	0	H
Page	admin	entete	conception	10	100%	10	0	H
Page	admin	footer	conception	2	100%	2	0	H
Page	admin	entete	html	10	50%		10
Page	admin	entete	css	15	50%		15
Page	logo	html		3	100%	3	0	M
Page	logo	css		15	50%		15	M
Page	admin	entete	html	5	100%	5	0
Page	admin	entete	css	15	50%		15
Page	admin	footer	html	5	100%	5	0
Page	admin	footer	css	15	50%		15

			Total	605		535	75